## Pricing
Phase | Weeks | Total Cost
Discovery | 2 | 51500
Foundations | 3 | 127800
Deployment | 4 | 161800
Monitoring | 6 | 217800
Enablement | 8 | 167200
Project Total | 23 | 726100

## WBS
| Discovery |  | Foundations |  |  | Deployment |  |  |  | Monitoring | [5 empty] | Enablement
Role | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15 | Week16 | Week17 | Week18 | Week19 | Week20 | Week21 | Week22 | Week23 | Total
ML Architect | 40 | 40 | 40 | 40 | 40 | 30 | 30 | 30 | 30 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 520
ML Engineer | 10 | 10 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 620
Data Engineer | 10 | 10 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 620
ML DevOps Architect | 20 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 30 | 30 | 30 | 30 | 30 | 30 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 660
Tech Business Analyst | 40 | 40 | 40 | 40 | 40 | 30 | 30 | 30 | 30 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 520
Project Manager | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 460
Client Enablement Lead | 0 | 0 | 10 | 10 | 10 | 20 | 20 | 20 | 20 | 30 | 30 | 30 | 30 | 30 | 30 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 610
[23 empty] | total | 4010
HL WBS | [6 empty] | Rate (10% Cont included) | total
Role | Discovery | Foundations | Deployment | Monitoring | Enablement | Total (hrs)
ML Architect | 40 | 40 | 30 | 20 | 10 | 520 | 225 | 117000
ML Engineer | 10 | 40 | 40 | 40 | 10 | 620 | 200 | 124000
Data Engineer | 10 | 40 | 40 | 40 | 10 | 620 | 175 | 108500
ML DevOps Architect | 20 | 40 | 40 | 30 | 20 | 660 | 200 | 132000
Tech Business Analyst | 40 | 40 | 30 | 20 | 10 | 520 | 150 | 78000
Project Manager | 20 | 20 | 20 | 20 | 20 | 460 | 150 | 69000
Client Enablement Lead | 0 | 10 | 20 | 30 | 40 | 610 | 160 | 97600
[7 empty] | Sub-Total | 726100

## HL Timeline
TIMELINE TEMPLATES by Vertex42.com
https://www.vertex42.com/ExcelTemplates/timeline.html
Tips for Using this Template
• Insert and delete entire rows when editing the data tables
• Avoid leaving the label column blank
• Format the horizontal axis to set min/max bounds
• Enter a vertical position between -100 and 50
• Format individual data labels or markers to highlight specific events
Other Notes
• Milestone leader lines are Y Error bars
• Task leader lines are Y Error bars
• Task durations are X Error bars
Tasks
Start | End | Duration | Label | Vert. Position | Vert. Line
2025-07-07 | 2025-07-21 | 15 | Discovery & Current State Review Jul 7 - Jul 21 | -25 | -25
2025-07-21 | 2025-08-09 | 20 | Phase 1: MLOps Foundations Jul 21 - Aug 9 | -40 | -15
2025-08-11 | 2025-09-03 | 24 | Phase 2: Deployment & Integration Aug 11 - Sep 3 | -55 | -15
2025-09-08 | 2025-11-22 | 76 | Phase 3: Monitoring & Feedback Sep 8 - Nov 22 | -80 | -80
2025-09-24 | 2025-10-13 | 20 | Enablement & Client Handoff Sep 24 - Oct 13 | -30 | -30
Insert new rows above this one
Milestones
Date |  |  | Label | Position
2025-07-07 |  |  | Start, Monday July 7 | 30
2025-07-21 |  |  | End Discovery | 25
2025-08-15 |  |  | Phase 1 Complete | 20
2025-09-12 |  |  | Phase 2 Complete | 15
2025-09-26 |  |  | Phase 3 Complete | 10
2025-12-02 |  |  | Final Handoff | 5
Insert new rows above this one
Formulas:
End = [Start]+[Duration]-1

## HL Tasks
Tasks
Start | End | Duration (Days) | Label | Vert. Position | Vert. Line
2025-07-07 | 2025-07-21 | 11 | Discovery & Current State Review | -20 | -20
2025-07-21 | 2025-08-15 | 20 | Phase 1: MLOps Foundations | -40 | -20
2025-08-11 | 2025-09-12 | 25 | Phase 2: Deployment & Integration | -60 | -30
2025-09-08 | 2025-09-26 | 15 | Phase 3: Monitoring & Feedback | -30 | -30
2025-09-24 | 2025-12-02 | 50 | Enablement & Client Handoff | -50 | -20
Formulas:
End = WORKDAY([Start], [Duration (Days)] - 1)
Start = IF(WEEKDAY([Start, row above]+[Duration (Days), row above]+1, 2)>5, [Start, row above]+[Duration (Days), row above]+1+(8-WEEKDAY([Start, row above]+[Duration (Days), row above]+1, 2)), [Start, row above]+[Duration (Days), row above]+1)

## HL Milestones
Milestones
Date | Label | Position
2025-07-07 | Start, Monday July 7 | 30
2025-07-21 | End Discovery | 25
2025-08-15 | Phase 1 Complete | 20
2025-09-12 | Phase 2 Complete | 15
2025-09-26 | Phase 3 Complete | 10
2025-12-02 | Final Handoff | 5

## Detailed Timeline
TIMELINE TEMPLATES by Vertex42.com
https://www.vertex42.com/ExcelTemplates/timeline.html
Tips for Using this Template
• Insert and delete entire rows when editing the data tables
• Avoid leaving the label column blank
• Format the horizontal axis to set min/max bounds
• Enter a vertical position between -100 and 50
• Format individual data labels or markers to highlight specific events
Other Notes
• Milestone leader lines are Y Error bars
• Task leader lines are Y Error bars
• Task durations are X Error bars
Tasks
Start | End | Duration | Label | Vert. Position | Vert. Line
2025-07-07 | 2025-07-11 | 5 | Kickoff & Stakeholder Alignment | -20 | -50
2025-07-14 | 2025-07-19 | 6 | Current ML System Assessment | -20 | -20
2025-07-21 | 2025-07-28 | 8 | Model Containerization (Docker) | -40 | -20
2025-07-29 | 2025-08-08 | 11 | CI/CD Pipeline Setup (GitHub Actions) | -40 | -20
2025-08-11 | 2025-08-15 | 5 | Model Registry Setup (MLflow) | -60 | -30
2025-08-18 | 2025-08-22 | 5 | Feature Store Setup (Feast) | -60 | -30
2025-08-25 | 2025-09-01 | 8 | Security & IAM Configuration | -60 | -30
2025-09-02 | 2025-09-06 | 5 | Integration Testing in Staging Env | -30 | -30
2025-09-08 | 2025-09-13 | 6 | Deploy Real-Time Models w/ KServe | -30 | -30
2025-09-15 | 2025-09-20 | 6 | Deploy Batch Models w/ Airflow | -50 | -20
2025-09-22 | 2025-09-26 | 5 | API Integration with CRM & Inventory | -50 | -20
2025-09-29 | 2025-10-03 | 5 | Monitoring Setup (Prometheus, Grafana) | -50 | -20
2025-10-06 | 2025-10-10 | 5 | Drift Detection Setup (WhyLabs) | -50 | -20
2025-10-13 | 2025-10-17 | 5 | Alerting & Audit Logging | -50 | -20
2025-10-20 | 2025-10-24 | 5 | Retraining Pipeline Setup (Airflow) | -50 | -20
2025-10-27 | 2025-10-31 | 5 | Shadow Deployments & A/B Testing | -50 | -20
2025-11-03 | 2025-11-07 | 5 | Documentation & Knowledge Transfer | -50 | -20
2025-11-10 | 2025-11-14 | 5 | Final Handoff & Stakeholder Sign-off | -50 | -20
Insert new rows above this one
Milestones
Date |  |  | Label | Position
2025-07-07 |  |  | Start, Monday July 7 | 30
2025-07-21 |  |  | End Discovery | 25
2025-08-15 |  |  | Phase 1 Complete | 20
2025-09-12 |  |  | Phase 2 Complete | 15
2025-09-26 |  |  | Phase 3 Complete | 10
2025-12-02 |  |  | Final Handoff | 5
Insert new rows above this one
Formulas:
End = [Start]+[Duration]-1

## Detailed Tasks
Detailed Tasks
Start | End | Duration | Label | Vert. Position | Vert. Line
2025-07-07 | 2025-07-11 | 5 | Kickoff & Stakeholder Alignment | -20 | -20
2025-07-14 | 2025-07-21 | 6 | Current ML System Assessment | -20 | -20
2025-07-21 | 2025-07-30 | 8 | Model Containerization (Docker) | -40 | -20
2025-07-29 | 2025-08-12 | 11 | CI/CD Pipeline Setup (GitHub Actions) | -40 | -20
2025-08-11 | 2025-08-15 | 5 | Model Registry Setup (MLflow) | -60 | -30
2025-08-18 | 2025-08-22 | 5 | Feature Store Setup (Feast) | -60 | -30
2025-08-25 | 2025-09-03 | 8 | Security & IAM Configuration | -60 | -30
2025-09-02 | 2025-09-08 | 5 | Integration Testing in Staging Env | -30 | -30
2025-09-08 | 2025-09-15 | 6 | Deploy Real-Time Models w/ KServe | -30 | -30
2025-09-15 | 2025-09-22 | 6 | Deploy Batch Models w/ Airflow | -50 | -20
2025-09-22 | 2025-09-26 | 5 | API Integration with CRM & Inventory | -50 | -20
2025-09-29 | 2025-10-03 | 5 | Monitoring Setup (Prometheus, Grafana) | -50 | -20
2025-10-06 | 2025-10-10 | 5 | Drift Detection Setup (WhyLabs) | -50 | -20
2025-10-13 | 2025-10-17 | 5 | Alerting & Audit Logging | -50 | -20
2025-10-20 | 2025-10-24 | 5 | Retraining Pipeline Setup (Airflow) | -50 | -20
2025-10-27 | 2025-10-31 | 5 | Shadow Deployments & A/B Testing | -50 | -20
2025-11-03 | 2025-11-07 | 5 | Documentation & Knowledge Transfer | -50 | -20
2025-11-10 | 2025-11-14 | 5 | Final Handoff & Stakeholder Sign-off | -50 | -20
Formulas:
Start = IF(WEEKDAY([Start, row above]+[Duration, row above], 2)>5, [Start, row above]+[Duration, row above]+(8-WEEKDAY([Start, row above]+[Duration, row above], 2)), [Start, row above]+[Duration, row above])
End = WORKDAY([Start], [Duration] - 1)

## Detailed Milestones
Sprint | Sprint (Week) | Milestone | Description
Sprint 1 | Week 1 | Model Artifact Assessment | Review existing model code, data formats, and dependencies
| Week 2 | Environment Audit | Audit current infrastructure (cloud/on-prem, APIs, data pipelines)
Sprint 2 | Week 3 | Containerization Setup | Containerize models using Docker/Conda for reproducibility
| Week 4 | CI/CD Pipeline Setup | Create GitHub Actions/Jenkins pipelines for build and deploy
Sprint 3 | Week 5 | Model Registry Configuration | Set up MLflow or SageMaker registry with versioning
| Week 6 | Feature Store Planning | Design real-time and batch feature store approach
Sprint 4 | Week 7 | Security Framework | IAM roles, secrets mgmt, audit logging policy
| Week 8 | Real-Time Inference Infra | Deploy KServe endpoints for fraud/recs with autoscaling
Sprint 5 | Week 9 | Batch Pipeline Setup | Configure Airflow/Dagster for pricing/segmentation jobs
| Week 10 | System Integration | Integrate models with CRM, inventory, and frontend APIs
Sprint 6 | Week 11 | Monitoring Tools | Set up Prometheus, Grafana, WhyLabs for perf & drift tracking
| Week 12 | Alerting & Logging | Build alert workflows, compliance-grade audit logs
Sprint 7 | Week 13 | Retraining Logic | Airflow trigger setup for drift or scheduled retraining
| Week 14 | Shadow Deployment | Deploy A/B and shadow testing for model validation
Sprint 8 | Week 15 | User Acceptance Testing | Business stakeholder validation of predictions and outputs
| Week 16 | Production Launch | Final cutover to live traffic with rollback plan in place

## About (hidden)
PROJECT TIMELINE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-timeline.html
About This Template
This template uses a scatter chart with data labels and error bars to create a project timeline that shows both milestones and tasks with durations. Unlike a Gantt chart, which shows each task on a separate row, you control the vertical positioning of tasks within the timeline. You can specify the length of the vertical leader line to help show task dependencies.
This type of project timeline is mainly useful for a general overview of a project rather than showing a detailed work breakdown structure.
More Templates
Visit Vertex42.com to download other timeline and project management templates.
More Timeline Templates
More Project Management Templates
About Vertex42
Vertex42.com provides professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.